## Backlog
Features | Name | User Story Cards | Name | Feature
1 | Authentication | 1 | Sign In - Email | 1
2 | Screens | 2 | Sign In - Google | 1
3 | Core Functionality | 3 | Sign Up - Email | 1
|  | 4 | Sign Up - Google | 1
|  | 5 | JWT Authentication | 1
|  | 6 | Sign Out | 1
|  | 7 | Home Page | 2
|  | 8 | Browse Properties | 2
|  | 9 | Discover Properties - Frontend | 2
|  | 10 | Property Listing Details | 2
|  | 11 | User Profile Page | 2
|  | 12 | Search Filters | 3
|  | 13 | Search Terms | 3
|  | 14 | Sidebar | 2
|  | 15 | Location Information | 3
|  | 16 | Pagination | 3
|  | 17 | Events Tracking | 3
|  | 18 | Like Properties | 3
|  | 19 | Share Property | 3
|  | 20 | Contact Estate Agent | 3
|  | 21 | Estate Agent Profile | 2
|  | 22 | Edit Profile | 2

## USC 1
USC Number | 1
USC Name | Sign In - Email
Feature | 1 - Authentication
User Story:
As a registered user, I want to be able to sign in with my email and password, So that I can use the application AND only I can access my data
Description:
Within the application, users must sign in to their profile before being able to use any of the functionality. If they have created an account with an email and password, then they can provide these and the backend will verify that they match their account. If the details match then they will be authenticated within the app. The sign in screen should be the first screen that a user is taken to Frontend 1. User can enter email and password within Sign In screen in application 2. Application will make HTTP request to /user/login API route, with contents of email and password fields sent within request body. 3. If response code is 200: Set LoginModel currentUser to the user returned in response Set LoginModel isAuthenticated to True Save UserID and JWT (see USC 5) to userDefaults 4. If response code is not 200, then present error message to user Backend: /user/login API route 1. Decode request body to email and password variables 2 Find user in database for provided email 3. If user does not exist, return 404 authentication error 4. If user account found, hash provided password using Bcrypt and see if it matches password attached to user account 5. If password does not match, return 404 authentication error 6. If password does match, generate JWT (see USC 5) and return status 200, with user account and JWT in response body
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email and password WHEN: I enter my correct email and password within the sign in screen THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 5
GIVEN: I have an account registered with my email and password WHEN: I enter my details incorrectly THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen

## USC 2
USC Number | 2
USC Name | Sign In - Google
Feature | 1 - Authentication
User Story:
As a registered user with a Google account, I want to be able to sign in using Google, So that I can use the application AND only I can access my data
Description:
Within the application, users must sign in to their profile before being able to use any of the functionality. If they have created an account with an email and password, or through Google, then they can sign in with Google in order to verify their identity. If they sucesfully sign in with Google, the backend will retrieve the users information so they can be logged in within the app Frontend 1. User can select Sign In with Google on sign in page within the application 2. Application will present Google sign in page 3. If Sign In with Google is successful, Google will return authentication token and application will make HTTP request to /user/googleLogin API route, with authenticaton token included within request body. 4. If response code is 200: Set LoginModel currentUser to the user returned in response Set LoginModel isAuthenticated to True Save UserID and JWT (see USC 5) to userDefaults 45 If response code is not 200, then present error message to user Backend: /user/googleLogin API route 1. Decode Google idToken from request body 2. Retrieve Google account details using Google OAuth2 library 3. Find user in database for provided email 4. If user does not exist, create account using email, name and image from Google account 5. If user account found, generate JWT (see USC 5) and return status 200, with user account and JWT in response body
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email WHEN: I select Sign In with Google AND: Provide the correct details THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 5
GIVEN: I have an account registered with my email WHEN: I select Sign In with Google AND: Provide the incorrect details THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen
GIVEN: I do not have an account registered with my email WHEN: I select Sign In with Google AND: Provide the correct details THEN: An account will be created using the details of my Google account AND: I will be signed in to my account AND: I will be taken to the home screen

## USC 3
USC Number | 3
USC Name | Sign Up - Email
Feature | 1 - Authentication
User Story:
As a new user, I want to be able to sign up for an account, So that I can use the application AND my data can be remembered
Description:
Within the application, users must first create an account so that they can save their details and verify their identity. If they request to create an account, they will first be asked to input all of the required fields for creating an account, and then also given the option to add addtional account information. This will then be sent to the backend, and if successful then an account will be created for them and they will automatically be signed in. Frontend 1. User is first asked to input name, email, password and confirm password 2. When user presses continue, fields will be verified to ensure the input is valid, and make HTTP request to /user/checkEmail route to ensure that no account exists alreadt 3. If everything is valid, they will be taken to next screen, or if not they will be given an appropriate warning message 4. User is then given the chance to add Profile Picture, date of birth, phone number, about info. 5. If user tries to sign up, fields are then verified again and application will make HTTP request to user/signUp route, including all entered information in the request body. 6. If response code is 200: Set LoginModel currentUser to the user returned in response Set LoginModel isAuthenticated to True Save UserID and JWT (see USC 5) to userDefaults 7. If response code is not 200, then present error message to user Backend: /user/signUp API route 1. Decode request body to corresponding variables 2 Check that user does not exist in database for provided email 3. If user does exist, return 404 authentication error 4. If user does not exst, hash provided password using Bcrypt and create a new User object with all of the provided details, setting the isAgent field to false 5. Store user account in database, generate JWT (see USC 5) and return status 200, with user account and JWT in response body /user/checkEmail API route 1. Check if user account exists for user ID contained in request parameters 2. Return true or false accordingly
Acceptance Criteria |  | Dependencies
GIVEN:There is an account registered with an email WHEN: I enter the email in the sign up screen THEN: I will not be able to proceed AND: I will be notified that an account already exists |  | 5
GIVEN: I have entered passwords that do not match within the sign up screen WHEN: I try to proceed THEN: I will be notified that the passwords do not match
GIVEN: I have entered an invalid name, email, or password within the sign up screen WHEN: I try to proceed THEN: I will be notified about the invalid field
GIVEN: I have entered a valid name, email and password within the sign up screen WHEN: I click continue THEN: I will be taken to the next screen
GIVEN: I am on the About You section of the sign up screen AND: Have not entered an invalid mobile number WHEN: I click continue THEN: An account will be created in the database with the data entered AND: I will be signed in to my account AND: I will be taken to the home screen

## USC 4
USC Number | 4
USC Name | Sign Up - Google
Feature | 1 - Authentication
User Story:
As a new user who has signed up with Google, I want to be able to add additional details to my account, So that my profile contains more information about me
Description:
Within the application, users must first create an account so that they can save their details and verify their identity. If they sign in with Google and do not have an account, an account will be created automatically as per USC 3. If this is the case, they should also be given the option to add additional account information in line with the standard sign up process. This will then be sent to the backend and added to their account, before they are signed in for the first time. Frontend 1. User signs in with Google for the first time. 2. When user completes sign in, as per USC 2, the backend should return a flag that a new account has been created, alongside their account information and token. 3. If this flag is true, they should be taken to the second part of the Sign Up process, where they can choose to add their date of birth, change their profile picture, add their mobile number and add details to their about section 4. When user presses Continue, the application will make HTTP request to user/updateProfile route, including all entered information in the request body 5. If response code is 200: Update LoginModel currentUser to the user returned in response 7. If response code is not 200, then present error message to user Backend: /user/updateProfile API route 1. Decode request body to corresponding variables 2 Use FindAndUpdate method to find the users profile and update each of the fields that have been changed 3. Return status 200, with updated user account in request body
Acceptance Criteria |  | Dependencies
GIVEN: I have not got an account registered with my email WHEN: I sign in with Google THEN: I will be given the option to add additional information to my profile |  | 2
GIVEN: I have not got an account registered with my email WHEN: I sign in with Google AND: I provide additional profile details THEN: These will be added to my profile

## USC 5
USC Number | 5
USC Name | JWT Authentication
Feature | 1 - Authentication
User Story:
As a system admin, I want to ensure that only authenticated users can make certain API calls So that the system is secure fro unauthorised access
Description:
In order to verify the authenticity of a signed in user and requests made, the backend will use JWT authentication to protect certain API endpoints. This means the backend can verify that the call is coming from a user who has been officially signed in, and stop unauthorised users from accessing or changing application data outside of the app or without permission. Frontend 1. When a user signs into their account, the backend will return a JWT authentication token. This can be stored in the local userDefaults and included in the Authorization header of future API calls to validate to the backend that they have been signed in Backend: Generate JWT - used during sign in Using the JWT library, the user's ID can be signed using a secret key from the backend to generate a JWT. This can be decrypted by the backend to prove that the user has officially signed in through the system, as a malicious user would not be able to sign a user ID with the correct key. Authenticate Function - can be used to protect certain API endpoints to verify that they are being accessed by signed in user 1. Use JWT Verify function to decrypt JWT using secret key 2. Check user exists with ID contained in JWT 3. Allow access to function (next) or return error message in response
Acceptance Criteria |  | Dependencies

## USC 6
USC Number | 6
USC Name | Sign Out
Feature | 1 - Authentication
User Story:
As a logged in user, I want to be able to sign out of my account So that another account can be logged into
Description:
Signing out of the application is a relatively simple process. First, any user variables from view models must be cleared, and then any persisted data should be removed (from userDefaults) Frontend 1. When the user presses the Sign Out button located in the sidebar (USC 14), the LoginViewController isAuthenticated value should be set to False and the currentUser should be set to nil 2. All persisted data in userDefaults should be cleared (JWT, user filters, userID) 3. The user should be taken to the login screen
Acceptance Criteria |  | Dependencies
GIVEN: I am signed in to an account WHEN: I select Sign Out THEN: I will be returned to the home screen |  | 1, 14
GIVEN: I have signed out of an accoujt WHEN: I sign in to another account THEN: No data from the previous account will be shown

## USC 7
USC Number | 7
USC Name | Home Page
Feature | 2 - Screens
User Story:
As a signed in user I want to be presented with a home screen So that I can see an overview of the application
Description:
After signing into the app, users will first be taken to a home screen which gives them an overview of some of the property information within the app and gives them access to some of the core functionality Frontend 1. Show an overview of recently added properties (same data as USC 8 - Browse Properties) 2. Allow user to change filters (functionality from USC 12 - Filters) which effect Browse preview 3. Show an overview of recommended properties (same data as USC 9 - Discover Properties) 4. Allow users to select properties to be taken to full details (USC 10 - Listing Details) 5. Allow user to enter Search phrase to be used for Browse Properties functionality (USC 13 - Search terms)
Acceptance Criteria |  | Dependencies
GIVEN: I am signed into the application WHEN: I am viewing the home screen THEN: I should be shown recently added properties that match my search criteria |  | 8,9,10,12,13
GIVEN: I am signed into the application WHEN: I am viewing the home screen THEN: I should be shown properties that have been provided by the recommender system
GIVEN: I am signed into the application WHEN: I select a property from the home screen THEN: I should be taken to the full listing details page
GIVEN: I am signed into the application WHEN: I am viewing the home screen THEN: I should be able to modify my search filters
GIVEN: I am signed into the application WHEN: I am viewing the home screen THEN: I should be able to add a search term AND: Be taken to the Browse screen

## USC 8
USC Number | 8
USC Name | Browse Properties
Feature | 2 - Screens
User Story:
As a signed in user I want to be able to Browse all properties in the database So that I can view information about properties that I am interested in
Description:
When a user is on the Browse page, they should be presented with properties that meet their search criteria. If there is no criteria added, this should just load all properties and present them in order of most recently added. Frontend 1. HTTP request should be made to backend, including any search criteria (as per USC 12 and USC 13), and the users token from userDefaults 2. The properties contained within the response should then be decoded and appended to the PropertyViewModel properties array. 3. For each property contained within the PropertyViewModel, a preview should be displayed inline with the UI mockup (include distance as per USC 15). If this is selected then the user should be presented with a full listing view (USC 10) Backend /listing API route (Requires JWT) 1. Decode filters and search terms from request to local variables 2 Use filters to build MongoDB aggregation pipeline ( match.price = { $gte: filters.minPrice, $lte: filters.maxPrice };) etc 3. Retrieve listings from database using .aggregate call, including match variable to filter, sorting by most recent, and limiting to 10 results (pagination to be implemented in USC 16) 4. If properties found, return status 202 and properties in response body 5. If no properties found, return status 404.
Acceptance Criteria |  | Dependencies
GIVEN: I have set no search criteria WHEN: I view the Browse page THEN: I will be presented with the 10 most recently added property listings |  | 12,13,10
GIVEN: I have set search criteria WHEN: I view the Browse page THEN: I will be presented with the 10 most recently added property listings that fit these criteria

## USC 9
USC Number | 9
USC Name | Discover Properties - Frontend
Feature | 2 - Screens
User Story:
As a signed in user I want to be able to access property recommendations So that I can easily find properties that are of interest to me
Description:
In the Discover page, users should be provided with recommended properties in the format of proeprty cards which they can swipe through, indicating their preference about the property. They should be able to select a card to view more information, and also view information about how the recommendation screen works. Frontend 1. Initially any properties shown to the user should be noted and their ID should be stored locally. This will be built out further with USC 17 - Events Tracking 2. HTTP request should be made to backend, including any search filters (as per USC 12), the properties that the user has viewed in this session, and the users token from userDefaults (seperate request for CF and CBF recommender) 2. The properties contained within the response should then be decoded to the DiscoverViewModel CF and CBF arrays. 3. Depending on the setting they have selected (in Information screen), they should be presented with a stack of property cards which show information about each of the properties from either the CF or CBF recommender. 4. If a user swipes left, it should dismiss the property 5. If a user swipes right, the property should be liked (USC 18 - Like Properties), the user should be given visiual feedback, and the property should then be dismissed 6. If the user likes a property using the CBF recommender, a new request should be made to the backend and the recommendations should be replaced 7. Once all recommendations have been viewed, a new request should be made to get more recommendations 8. If a user taps the image of a property card, this should cycle through the images attached to the listing 9. If the user selects the body of the property card, they should be taken to the full details of the listing
Acceptance Criteria |  | Dependencies
GIVEN: I am signed into my account WHEN: I am viewing the Discover property screen THEN: I will be be presented with a card stack of recommendations |  | 17, 18
GIVEN: I am signed into my account WHEN: I am viewing the Discover property screen AND: I swipe left THEN: The property card will animate to the left AND: The next property will be shown
GIVEN: I am signed into my account WHEN: I am viewing the Discover property screen AND: I swipe left THEN: The property card will animate to the right AND: The property will be liked AND: The next property will be shown
GIVEN: I am signed into my account WHEN: I am viewing the Discover property screen AND: I swipe in either direction THEN: It will be logged within the app that I have seen that property
GIVEN: I am viewing the Discover property screen WHEN: I select the Info button THEN: A popup will be shown which gives information about the recommendation system
GIVEN: I am viewing the Discover property screen WHEN: I select the Filter button THEN: I will be able to modify my search filters
GIVEN: I am viewing the Discover property screen WHEN: I have viewed all loaded properties THEN: More recommendations should be loaded and displayed

## USC 10
USC Number | 10
USC Name | Property Listing Details
Feature | 2 - Screens
User Story:
As a signed in user I want to be able to view the full details of a property So that I can find out whether it is suitable for me
Description:
When a user selects a property listing, they should be taken to a page which contains the full details of the propery listing Frontend 1. When a user selects a property preview from another screen, the Property object should be passed to a full details view 2. The information associated with the property should be displayed inline with the UI mockup 3. The images associated with the property should be able to be swiped through in a gallery style at the top of the screen 4. The location button functionality is covered in USC 15 5. The like button functionality is covered in USC 18 6. The contact agent functionlity is covered in USC 20 7. The share functionality is covered in USC 19 8. If the Estate Agent name is selected, the user should be taken to their profile (USC 21)
Acceptance Criteria |  | Dependencies
GIVEN: I selected a property preview from another screen WHEN: I am shown the full details of the property THEN: The following fields should be visible (if avaliable) Address Estate Agent Bedrooms Bathrooms Size Description Images Location Price |  | 18, 15

## USC 11
USC Number | 11
USC Name | User Profile Page
Feature | 2 - Screens
User Story:
As a signed in user I want to be able to view information about my profile So that I can see what properties I have liked
Description:
When a user goes to their profile page, they should be details of their profile as follows. The User's profile should be passed to the viewModel from the loginViewModel currentUser variable. Frontend 1. The user's name, profile picture, and about section should be shown at the top of the page 2. They should be able to press the Edit Profile button to edit their profile details (USC 22) 3. The properties that the user has liked should be shown in the My Collection section. 4. The My Collection section should be displayed as a grid or list, depending on what the user selects Backend /like/{userid} API route: 1. Query likes database for entries matching userId from path variable, in order of timestamp 2. Make array of each listingId that the user has liked 3. Query listing database to get details of all listings that user has liked, and sort by order of index in liked Array { $addFields: { "__order" : { "$indexOfArray" : [ listingIds, "$_id" ] } }}, { $sort: { "__order": 1 }} 4. Return liked properties
Acceptance Criteria |  | Dependencies
GIVEN: I am signed in WHEN: I view my profile screen THEN: I should see my Profile picture. Name and about section |  | 22
GIVEN: I am signed in WHEN: I view my profile screen THEN: I should see all of the properties that I have liked, in the order that they were liked (most recent first)
GIVEN: I am signed in WHEN: I view my profile screen THEN: I should be able to select a property that I have liked to view the full details
GIVEN: I am signed in WHEN: I view my profile screen THEN: I should be able to change the My Collection section between a grid and list view
GIVEN: I am signed in WHEN: I view my profile screen THEN: I should be able to click the Edit Profile button to be taken to the Edit Profile screen (USC 22)

## USC 12
USC Number | 12
USC Name | Search Filters
Feature | 3 - Core Functionality
User Story:
As a signed in user I want to be able to add search filters So that I can refine the results that I am shown
Description:
Users should be able to add search filters to refine their search within various parts of the application. The filters should be stored locally in userDefaults, and the same set of filters apply to all views where filters are used Frontend 1. Filters view should be presented as a popover 2. The user should be able to select mutliple Property Types, from all of the options that are assigned to properties in the database, or select Any (which will deselect all property types) 3. The user should be able to select a price per month using a slider to set a value between 0 and 20,000, or click the text to type in a value manually which can be outside of this range 4. The user should be able to select a number of bedrooms and bathrooms. If they select two values, the values inbetween this range should be automatically selected. 5. The property size should be set with a slider that works the same as the Price slider, with the standard range between 0 and 3000 6. If the user selects reset, all values should be deselected/set to any and the sliders should be set to their upper and lower bound 7. If the user presses cancel, any changes made should not be saved 8. If the user presses Show Listings, the filters should all be saved to UserDefaults and the current view should refresh its properties from the backend
Acceptance Criteria |  | Dependencies
GIVEN: I am signed in WHEN: I select the Flters icon THEN: A popover view should be presented
GIVEN: I am viewng the Filters screen WHEN: I have previously saved Filters THEN: The values that I have selected before should be shown
GIVEN: I am viewng the Filters screen WHEN: I select Any for Property Type/Bedrooms/Bathrooms THEN: All other values for the corresponding field should be deselected AND: Any should be highlighted
GIVEN: I am viewng the Filters screen WHEN: I drag the handles for the Price or Property size slider THEN: The handles should not overlap AND: The value above the slider should update accordingly
GIVEN: I am viewng the Filters screen WHEN: I tap a value for the property type THEN: The value shoul be selected or deselected
GIVEN: I am viewng the Filters screen WHEN: I select a number of bedrooms or bathrooms THEN: The value should be selected/deselected accordingly AND: Any values inbetween/outside of the range should be selected/deselected
GIVEN: I am viewng the Filters screen WHEN: I press reset THEN: All values should be reset to their default values
GIVEN: I am viewng the Filters screen WHEN: I press cancel THEN: Any changes made to filters should not be saved
GIVEN: I am viewng the Filters screen WHEN: I select Show Listings THEN: The values I have selected should be saved to UserDefaults AND: The previous view should be refreshed

## USC 13
USC Number | 13
USC Name | Search Terms
Feature | 3 - Core Functionality
User Story:
As a signed in user I want to be able to be able to add Search Terms So that I can find properties that meet my criteria
Description:
When a user is on the Browse page, they should be presented with properties that meet their search criteria. If there is no criteria added, this should just load all properties and present them in order of most recently added. Frontend 1. HTTP request should be made to backend, including any search criteria (as per USC 12 and USC 13), and the users token from userDefaults 2. The properties contained within the response should then be decoded to the PropertyViewModel properties array. 3. For each property contained within the PropertyViewModel, a preview should be displayed inline with the UI mockup (include distance as per USC 15). If this is selected then the user should be presented with a full listing view (USC 10) 4. If user scrolls to bottom, fetch more results as per pagination functionality from USC 16 Backend
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email and password WHEN: I enter my correct email and password within the sign in screen THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 12,13,10,15,16
GIVEN: I have an account registered with my email and password WHEN: I enter my details incorrectly THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen

## USC 14
USC Number | 14
USC Name | Sidebar
Feature | 2 - Screens
User Story:
As a signed in user I want to be able to be able to navigate the app using a sidebar So that the navigation does not clutter my screen
Description:
When a user signed into the app, they should be able to view a pop out SideBar which gives them additional navigation options Requirements 1. When the user selects the menu button (top right), the current view should slide to the right as shown in the UI mockup, revealing a sidebar 2. If the user selects the exit button from the sidebar, the current view should slide left to cover the screen again 3. The user's profile picture and name should be shown with a navigation link to take them to their profile 4. Different tabs should be shown within the sidebar (Home, Inbox, Saved Properties, Settings, Help), and the currently selected tab should be highlighted as shown 5. If the user selects a different tab, the current view at the right should change and the selected tab in the Sidebar should animate to change which is highlighted 6. There should be a sign out button at the bottom of the Sidebar which will trigger functionality outlined in USC 6
Acceptance Criteria |  | Dependencies
GIVEN: I am signed in to the app WHEN: I select the menu icon THEN: The current view should slide to the right (animated) AND: The sidebar should be revealed |  | 6
GIVEN: I viewing the Sidebar WHEN: I select view profile THEN: The current view should change to my profile AND: The sidebar should be closed
GIVEN: I viewing the Sidebar WHEN: I select Sign Out THEN: I should be signed out as per USC 6
GIVEN: I viewing the Sidebar WHEN: I select a different tab THEN: The currently highlighted tab in the Sidebar should update (animated) AND: The view at the right should be switched accordingly

## USC 15
USC Number | 15
USC Name | Location Information
Feature | 3 - Core Functionality
User Story:
As a signed in user I want to be able to be able to be provided with information abot the location of a property So that I can decide whether it is suitable for me
Description:
Properties returned to the application include a latitude and longitude. This can be used with MapKit to provide location data to the user Frontend 1. When viewing the Property Listing details page (USC 10), if a user presses the location icon, they should be shown a small popover which dispalys the location of the property. Clicking outside of this should dismiss it. 2. When being shown a preview for a property (Home Page, Browse page etc), the distance between the user's location (see point 3) and the property should be displayed. 3. User should be able to set their current/desired location within their profile Use Apple MapKit functionality
Acceptance Criteria |  | Dependencies
GIVEN: I am viewing a property's details WHEN: I select the location icon THEN: I should be shown the location on an interactive map
GIVEN: I am logged into the app WHEN: I am viewing a preview for a property THEN: I should be able to see the distance between this property and my set location
GIVEN: I am viewing my profile WHEN: I view my settings THEN: I should be able to set a location as my current/preferred location

## USC 16
USC Number | 16
USC Name | Pagination
Feature | 3 - Core Functionality
User Story:
As user I want to be able to load more results as I scroll So that I can efficiently view all results
Description:
When a user is on a page where results are shown (Browse, Saved), the app should not load all results at once as this would require a huge amount of data. Instead, the system should load a smaller amount (10 for example), and once the user has scrolled through all of these then the app should load the next results and seamlessly add these to what have already been loaded. Frontend: 1. When the second last row of content is displayed within a scrolling view, the app should trigger a loadMore function. 2. The loadMore function should make a request the the backend including the currently loaded number of properties (these should be skipped) 3. The backend will return the next set of properties which shoul be appended to the existing set, and the view should be updated to include these Backend: 1. Retrieve skip from req body 2. Define limit per request 3. Retrieve listings using match then use aggregation to sort and skip listings: listings = await Listing.aggregate([ { $match: match }, { $sort: { "date_added": -1 }}, //To implement sort and skip { $skip: skip }, { $limit: limit }, ]);
Acceptance Criteria |  | Dependencies
GIVEN: I am viewing the Browse View or Saved Listings WHEN: I scroll to the penultimate row THEN: More results should be loaded (if avaliable) |  | 8

## USC 17
USC Number | 17
USC Name | Events Tracking
Feature | 3 - Core Functionality
User Story:
As a signed in user I want my activity within the application to be logged So that the system can use this information to tailor my content
Description:
When a user views a property, this should be tracked so that the system can use the information to provide analytics data and more tailored suggetions. When a user views a property, the rating should be calculated as per the table to the right. Ratings should be stored on the device and periodically sent to the backend to be stored within the database. Frontend: 1. On Listing View appear, start a Timer 2. Add boolean to track whether user has scrolled to bottom of view and how many images have been viewed 2. On Disappear Calculate Rating and Track Event (rating and view) 3. Periodically send CoreData to backend (include in POST Request body) Calculate Rating - Check if existing rating exists locally and if user has explicitly liked listing (check CoreData) Use flags to calculate rating according to table Track Event - For ratings, if rating returned isnt 0 then store to CoreData entity. If rating already exists then update the existing rating For views, check if view already exists. If yes, update Date and if no create new Core Data entity
Acceptance Criteria |  | Dependencies
GIVEN: I am viewing a property WHEN: I finish viewing the property THEN: This data should be stored within the app |  | 9, 10
GIVEN: I am viewing a property WHEN: I finish viewing the property THEN: A implicit rating should be calculated AND: This data should be stored within the app
GIVEN: I am viewing the Discover screen WHEN: The app requests more recommendations THEN: All of the current interactions should be sent to the backend AND: Deleted from the local data store

## USC 18
USC Number | 18
USC Name | Like Properties
Feature | 3 - Core Functionality
User Story:
As a signed in user I want to be able to Like a property So that I can find properties again that I am interested in
Description:
When a user is viewing a property listing or swiping within the Discover scren, they should be able to Like a property that they can later view from their profile. Frontend 1. HTTP request should be made to backend, including the user's ID and the property to Like/Unlike 2. Upon successful response of the HTTP request, the interface should visually indicate that the user has liked a property with a heart icon Backend 1. Query the database for an existing like from the user for the given listing 2. If adding a like, if there is no existing like then proceed with creating one. Otherwise return an error 3. If removing a like, if there is an existing like then remove the like from the database. Otherwise return an error.
Acceptance Criteria |  | Dependencies
GIVEN: I am viewing a property WHEN: I select the Like button THEN: A like should be added/removed in the database AND: The interface should reflect the status of whether the property is liked or not |  | 9,10

## USC 19
USC Number | 19
USC Name | Share Property
Feature | 3 - Core Functionality
User Story:
As a signed in user I want my activity within the application to be logged So that the system can use this information to tailor my content
Description:
When a user is on the Browse page, they should be presented with properties that meet their search criteria. If there is no criteria added, this should just load all properties and present them in order of most recently added. Frontend 1. HTTP request should be made to backend, including any search criteria (as per USC 12 and USC 13), and the users token from userDefaults 2. The properties contained within the response should then be decoded to the PropertyViewModel properties array. 3. For each property contained within the PropertyViewModel, a preview should be displayed inline with the UI mockup (include distance as per USC 15). If this is selected then the user should be presented with a full listing view (USC 10) 4. If user scrolls to bottom, fetch more results as per pagination functionality from USC 16 Backend
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email and password WHEN: I enter my correct email and password within the sign in screen THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 12,13,10,15,16
GIVEN: I have an account registered with my email and password WHEN: I enter my details incorrectly THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen

## USC 20
USC Number | 20
USC Name | Contact Estate Agent
Feature | 3 - Core Functionality
User Story:
As a signed in user I want my activity within the application to be logged So that the system can use this information to tailor my content
Description:
When a user is on the Browse page, they should be presented with properties that meet their search criteria. If there is no criteria added, this should just load all properties and present them in order of most recently added. Frontend 1. HTTP request should be made to backend, including any search criteria (as per USC 12 and USC 13), and the users token from userDefaults 2. The properties contained within the response should then be decoded to the PropertyViewModel properties array. 3. For each property contained within the PropertyViewModel, a preview should be displayed inline with the UI mockup (include distance as per USC 15). If this is selected then the user should be presented with a full listing view (USC 10) 4. If user scrolls to bottom, fetch more results as per pagination functionality from USC 16 Backend
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email and password WHEN: I enter my correct email and password within the sign in screen THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 12,13,10,15,16
GIVEN: I have an account registered with my email and password WHEN: I enter my details incorrectly THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen

## USC 21
USC Number | 21
USC Name | Estate Agent Profile
Feature | 2 - Screens
User Story:
As a signed in user I want my activity within the application to be logged So that the system can use this information to tailor my content
Description:
When a user is on the Browse page, they should be presented with properties that meet their search criteria. If there is no criteria added, this should just load all properties and present them in order of most recently added. Frontend 1. HTTP request should be made to backend, including any search criteria (as per USC 12 and USC 13), and the users token from userDefaults 2. The properties contained within the response should then be decoded to the PropertyViewModel properties array. 3. For each property contained within the PropertyViewModel, a preview should be displayed inline with the UI mockup (include distance as per USC 15). If this is selected then the user should be presented with a full listing view (USC 10) 4. If user scrolls to bottom, fetch more results as per pagination functionality from USC 16 Backend
Acceptance Criteria |  | Dependencies
GIVEN: I have an account registered with my email and password WHEN: I enter my correct email and password within the sign in screen THEN: I will be signed in to my account AND: I will be taken to the home screen |  | 12,13,10,15,16
GIVEN: I have an account registered with my email and password WHEN: I enter my details incorrectly THEN: I will be notified that there was a problem authenticating me AND: I will remain on the sign in screen